## Summary
Metric | Value
Total Hours | 1380
Total Project Value (ex GST) | 200000
Effective Blended Rate | 144.9275
Optional GST (10%)
Optional Total (inc GST)

## Scoping
Task | Description | Roles | Rate/HR | Time | Subtotal
Business Discovery Workshops | Facilitate stakeholder workshops to capture requirements and objectives | Business Analyst | 232.8093 | 24
Stakeholder Alignment Sessions | Run review loops to align commercial and delivery expectations | Product Manager | 232.8093 | 20
Workflow Mapping and ERD Planning | Map process flows and draft entity relationships for delivery scope | Business Analyst | 232.8093 | 26
Functional Specification Drafting | Document functional and non-functional requirements baseline | Business Analyst | 232.8093 | 18
Technical Feasibility and Risk Review | Assess constraints, risks, and architecture feasibility | Technical Lead | 232.8093 | 14
Project Milestones and Delivery Plan | Define phased milestones, dependencies, and approvals | Product Manager | 232.8093 | 10
Acceptance Criteria and Scope Lock | Finalize acceptance criteria and scope boundaries | Business Analyst | 232.8093 | 8
Section Total

## UX & Design
Task | Description | Roles | Rate/HR | Time | Subtotal
Low-Fidelity Wireframing | Prepare low-fidelity wireframes for primary product journeys | UI/UX Designer | 93.6038 | 28
High-Fidelity Figma Prototyping | Create high-fidelity interactive prototypes for core workflows | UI/UX Designer | 93.6038 | 46
Design System and Component Specs | Define typography, spacing, tokens, and reusable components | UI/UX Designer | 93.6038 | 34
Accessibility and UX Audit | Run accessibility and usability checks against key journeys | UI/UX Designer | 93.6038 | 20
Iteration and Stakeholder Feedback | Incorporate iterative feedback while preserving UX consistency | UI/UX Designer | 93.6038 | 22
Design Handoff and Annotated Specs | Deliver annotated handoff specs for engineering implementation | UI/UX Designer | 93.6038 | 20
Section Total

## Frontend
Task | Description | Roles | Rate/HR | Time | Subtotal
Core App Shell and Routing | Implement app shell, navigation, and route structure | Frontend Developer | 175.657 | 56
Role-Based Dashboard Implementation | Build role-specific dashboards and user experiences | Frontend Developer | 175.657 | 52
Lesson Runtime and Presentation UI | Implement lesson runtime views and presentation mode surfaces | Frontend Developer | 175.657 | 68
Admin Panels and Content Interfaces | Build admin content, settings, and data-management interfaces | Frontend Developer | 175.657 | 56
Shared Component Architecture | Create and harden reusable UI components and patterns | Frontend Developer | 175.657 | 44
State Management and Data Integration | Integrate API data flows and state orchestration patterns | Frontend Developer | 175.657 | 28
Responsive and Accessibility Compliance | Refine mobile/tablet responsiveness and accessibility standards | Frontend Developer | 175.657 | 16
Section Total

## Backend
Task | Description | Roles | Rate/HR | Time | Subtotal
Domain Schema and Service Initialization | Initialize backend domains, service boundaries, and persistence wiring | Backend Developer | 192.6477 | 44
API Route Implementation | Implement and secure API routes across product domains | Backend Developer | 192.6477 | 92
Business Logic and Validation Layers | Build validation, rules engines, and core domain logic | Backend Developer | 192.6477 | 70
Authentication and RBAC Controls | Implement authentication, authorization, and role permissions | Backend Developer | 192.6477 | 42
Reporting and Operational Endpoints | Create reporting and operational endpoints for admin workflows | Backend Developer | 192.6477 | 28
Performance and Query Hardening | Tune backend queries, caching decisions, and endpoint performance | Backend Developer | 192.6477 | 24
Section Total

## DevOps
Task | Description | Roles | Rate/HR | Time | Subtotal
CI/CD Pipeline Engineering | Establish automated build, test, and deploy pipelines | DevOps Engineer | 92.8037 | 30
Environment Strategy (Dev/Staging/Prod) | Configure environment structure and deployment promotion model | DevOps Engineer | 92.8037 | 20
Secret Management and Access Policies | Implement secrets handling and secure operational access controls | DevOps Engineer | 92.8037 | 16
Observability and Alerting Baseline | Set up logs, metrics, and alerting for production oversight | DevOps Engineer | 92.8037 | 18
Backup and Recovery Design | Define backup, restore, and operational resilience procedures | DevOps Engineer | 92.8037 | 14
Security Hardening and Runtime Policies | Apply platform hardening and runtime security controls | DevOps Engineer | 92.8037 | 22
Section Total

## QA and Testing
Task | Description | Roles | Rate/HR | Time | Subtotal
Test Plan and Coverage Matrix | Define test strategy, coverage matrix, and quality gates | QA Tester | 68.0027 | 18
Cross-Browser and Device Testing | Execute browser and device compatibility testing cycles | QA Tester | 68.0027 | 32
Regression Testing Cycles | Run regression passes across critical product workflows | QA Tester | 68.0027 | 36
Integration and API Test Verification | Validate cross-system integrations and API behaviors | QA Tester | 68.0027 | 20
UAT Facilitation and Defect Triage | Facilitate client UAT and triage/prioritize defects | QA Tester | 68.0027 | 22
Fix Verification and Sign-Off Testing | Retest fixes and prepare sign-off quality evidence | QA Tester | 68.0027 | 12
Section Total

## Deployment and Hosting
Task | Description | Roles | Rate/HR | Time | Subtotal
Supabase Production Setup | Configure Supabase auth, storage, policies, and production settings | DevOps Engineer | 104.0042 | 24
Vercel Runtime and Build Configuration | Set up Vercel environments, builds, and runtime constraints | DevOps Engineer | 104.0042 | 20
GitHub Workflow and Release Controls | Establish branch strategy and release workflow controls | DevOps Engineer | 104.0042 | 18
Domain, DNS, and SSL Cutover | Configure domains, DNS, certificates, and secure routing | DevOps Engineer | 104.0042 | 12
Production Release Coordination | Coordinate controlled production releases and verification | DevOps Engineer | 104.0042 | 16
Post-Release Monitoring and Rollback Readiness | Monitor production stability and rollback readiness plans | DevOps Engineer | 104.0042 | 10
Section Total

## Handover and Support
Task | Description | Roles | Rate/HR | Time | Subtotal
Admin and Team Training | Train administrators and key users on platform operations | Product Manager | 100.804 | 16
Documentation and Runbook Authoring | Prepare operational documentation and support runbooks | Technical Writer | 100.804 | 24
Architecture and Knowledge Transfer | Deliver technical architecture walkthrough and handover | Technical Lead | 100.804 | 16
Post-Launch Support Window | Provide structured post-launch issue resolution support | Backend Developer | 100.804 | 20
Hypercare Bug Fixes and Stabilization | Resolve early-production issues and stability improvements | Frontend Developer | 100.804 | 18
Support Plan and Handover Closure | Formalize support model and close project handover | Product Manager | 100.804 | 16
Section Total

## Rollup
Section | Hours | Subtotal
Scoping | 120 | 27937.12
UX & Design | 170 | 15912.64
Frontend | 320 | 56210.25
Backend | 300 | 57794.3
DevOps | 120 | 11136.45
QA and Testing | 140 | 9520.38
Deployment and Hosting | 100 | 10400.42
Handover and Support | 110 | 11088.44
TOTAL