BULLYPROOF — Change Request

Discipline costing & scope split · 23 June 2026 · all figures ex-GST

This costs the change request by discipline (one specialist per category) rather than a blended day-rate, and separates what was originally agreed from scope added afterwards. Man-hours cost basis for the whole request: $251,931 (2023 hours).

Headline: the originally-agreed work (content type + bug fixes) is ~$41,738 and stays on the committed ~6-week timeline. The additional scope added later is $220,094 at cost (50 items, 1765 hours) and needs its own schedule. The Brand Refresh (module M8) is now included at no charge as a goodwill gesture (~$9,300 of work), and is excluded from the chargeable additional total above.

# 1.  Cost by discipline

Hours estimated per item per discipline, summed across all 60 items, priced at current AU contract day rates (direct/company, ex-GST):

| Discipline | Hours | Days | Day rate | Cost |
| --- | --- | --- | --- | --- |
| Design / UX | 190 | 23.8 | $900 | $21,375 |
| Frontend (React/Next) | 732 | 91.5 | $1,000 | $91,500 |
| Backend | 823 | 102.9 | $1,050 | $108,019 |
| DevOps / Infra | 40 | 5.0 | $1,150 | $5,750 |
| PM / BA / Admin | 238 | 29.8 | $850 | $25,288 |
| TOTAL | 2023 | 252.9 |  | $251,931 |

Backend and Frontend dominate; DevOps and Design are light. Rates: Design $900, Frontend $1,000, Backend $1,050, DevOps $1,150, PM/Admin $850 per day — all editable in the companion workbook.

# 2.  Original agreement vs additional scope

Only the content-type switch and the bug fixes were in the original agreement. Everything else was added later and is billed separately, on its own timeline.

| Scope | Items | Hours | Cost basis | Note |
| --- | --- | --- | --- | --- |
| Original — bug fixes (39, 40, 51, 53) | 4 | 94 | $11,738 | Within the committed ~6 weeks |
| Original — content type (Item 18) | 1 | 84 | $30,000 | Agreed in writing (≤$30k). Cost basis ~$10,550. |
| Additional scope (added later) | 50 | 1765 | $220,094 | Not in the original agreement — billed on top, own timeline |
| Goodwill - Brand Refresh (M8), no charge | 1 | 78 | $9,300 value / $0 charged | Included free as a goodwill gesture; excluded from the chargeable total |

- Original agreement ≈ $41,738: content type at the agreed $30,000 plus 4 bug fixes (~$11,738 cost). Delivered within the committed ~6 weeks.

- Additional scope = 50 items, 1765 hours, $220,094 at cost. This is the bulk of the work and was not part of what was agreed.

- Item 41 (activity feed) is treated as additional, not a bug fix — two of its three buttons already work; the real work is building a new activity timeline.

# 3.  Reasonable, firm and realistic: the pricing band

The signed $30,000 for the content type is itself the strongest pricing signal: its delivery cost is only ~$10,550, so the client has already accepted roughly a 2.8× markup over cost on this work. Applying the same logic gives a defensible band:

| Basis | Additional scope | Whole program |
| --- | --- | --- |
| Cost floor (man-hours × market rate) | $220,094 | $251,931 |
| Value basis (Item-18 precedent, ×2.8) | $625,859 | $667,597 |

- Cost floor — the firm, conservative number: $220,094 for the additional scope ($251,931 whole program). Hard to argue down; it is market rate × honest hours.

- Value basis — what the client's own agreement implies: ~$625,859 for the additional scope. Not aggressive; it just applies the markup they already signed for one item to the rest.

- Recommendation: quote the additional scope on the cost-plus discipline basis as the floor, and hold the value figure as justified headroom in negotiation.

# 4.  Timeline

With one specialist per discipline working in parallel (~7 productive hours/day), calendar time is the longest single queue, not the sum of all hours:

- Original agreement (content + bugs): ~6 weeks, as committed.

- Full additional scope: backend is the critical path at ~24 weeks (823 hours). Frontend ~21 weeks. So the additional scope is a ~24-week (≈5.4-month) program with parallel help, or proportionally longer solo.

- Practical implication: the additional scope cannot be absorbed into the original 6-week window. It is a separate phase with its own schedule and price.

Figures are indicative engineering effort for scoping, ex-GST (add 10% on invoice), and exclude content authoring, UAT and project management unless noted. Full per-item discipline hours are in the companion workbook “Bullyproof-Change-Request-Costing.xlsx”.