## Rates
Discipline rates & assumptions
Discipline | Day rate (AUD) | Hourly (AUD)
Design / UX | 900
Frontend (React/Next) | 1000
Backend | 1050
DevOps / Infra | 1150
PM / BA / Admin | 850
Hours per day | 8
Note
AU FY25/26 market contract rates, billed direct as a company (ex-GST; add 10% on invoice). Edit the day rates above — every figure in the Items and Summary sheets recalculates. Hours assume one specialist per discipline working in parallel.

## Items
Item | Section | Feature | Scope | Status | Design h | Frontend h | Backend h | DevOps h | PM/Admin h | Total h | Cost (AUD) | Notes
1 | A. Admin — Home / Dashboard | Admin landing / dashboard (to be replaced) | Done/— | EXISTS | 0 | 0 | 0 | 0 | 0
2 | A. Admin — Home / Dashboard | Total Schools vs Active (onboarding-complete) Schools | Additional | PARTIAL | 3 | 8 | 10 | 0 | 2
3 | A. Admin — Home / Dashboard | Per-school schedule status (On / Ahead / Slightly Behind / Behind) | Additional | MISSING | 8 | 20 | 30 | 4 | 8
4 | A. Admin — Home / Dashboard | “This School Year” / program-year selector (multi-year) | Additional | MISSING | 4 | 16 | 16 | 0 | 4
5 | A. Admin — Home / Dashboard | Data model: each school’s initial year vs ongoing years | Additional | MISSING | 2 | 4 | 40 | 6 | 6
6 | A. Admin — Home / Dashboard | Sidebar items: Manage Schools / Lessons / AP Cert / Users | Additional | EXISTS | 0 | 5 | 0 | 0 | 1
7 | A. Admin — Home / Dashboard | Dashboard filters: state, school level, sector, AP level, status | Additional | PARTIAL | 3 | 14 | 6 | 0 | 2
8 | A. Admin — Home / Dashboard | Dashboard columns (Culture trend, AP Cert %, Students, Classes, Teacher History, Lessons %, Schedule, Last Activity, Action) | Additional | PARTIAL | 6 | 28 | 30 | 0 | 6
9 | A. Admin — Home / Dashboard | Drill-downs: Onboarding, Culture, AP Cert detail, Class, Lesson History, Teacher History | Additional | PARTIAL | 8 | 28 | 28 | 0 | 6
10 | B. School Terms / Schedule Engine | Settings → School Terms (per-state term dates, per year, annual reset) | Additional | MISSING | 4 | 16 | 20 | 4 | 4
11 | B. School Terms / Schedule Engine | Term entry form (year/state/term dropdowns, date pickers, end-before-start validation) | Additional | MISSING | 3 | 14 | 6 | 0 | 2
12 | B. School Terms / Schedule Engine | Schedule calculation engine (progress vs Term 2 cadence, by state terms) | Additional | MISSING | 2 | 6 | 60 | 6 | 8
13 | B. School Terms / Schedule Engine | “Progress to End of Term 2” widget (current week, % elapsed by school days) | Additional | MISSING | 4 | 14 | 6 | 0 | 1
14 | C. Culture Rating | Data entry inputs (school days, attendance, absences, incidents, suspensions S/L, exclusions) | Additional | EXISTS | 0 | 4 | 2 | 0 | 1
15 | C. Culture Rating | Calculation / formulas with zero-input weighting | Additional | PARTIAL | 2 | 4 | 16 | 0 | 3
16 | C. Culture Rating | Benchmark + comparative periods (storage, rules: ≥20 days, overlap, post-program) | Additional | PARTIAL | 1 | 3 | 18 | 0 | 3
17 | C. Culture Rating | UX: comparative-period dropdown + speedometer (±100%, expandable to 150/200%) | Additional | PARTIAL | 8 | 14 | 2 | 0 | 1
18 | D. Content Types (Multi-Curriculum) | Add new Content Types / curricula (name, level count, level names) | Original | MISSING | 8 | 28 | 36 | 4 | 8 |  |  | Agreed price $30,000 (value-priced; ~$10,550 at cost)
19 | D. Content Types (Multi-Curriculum) | Per-content-type lesson creation / upload | Additional | PARTIAL | 4 | 24 | 16 | 0 | 4
20 | D. Content Types (Multi-Curriculum) | Content Type dropdown on Add New School | Additional | MISSING | 2 | 10 | 8 | 0 | 2
21 | D. Content Types (Multi-Curriculum) | Per-content-type resources | Additional | PARTIAL | 2 | 8 | 12 | 0 | 2
22 | E. Content Management / Security | MFA on content edits (email verification code before saving) | Additional | MISSING | 0 | 6 | 16 | 2 | 2
23 | E. Content Management / Security | Sole-content-editor / content-edit permission model | Additional | PARTIAL | 0 | 6 | 12 | 0 | 2
24 | E. Content Management / Security | Content audit log (create/edit/delete; date, user, event, content, version; comments) | Additional | MISSING | 2 | 14 | 28 | 0 | 4
25 | E. Content Management / Security | Version numbers + last-updated/updated-by per lesson/module; report; read-only retention | Additional | MISSING | 0 | 12 | 30 | 2 | 4
26 | F. Getting Started Videos | Role-based getting-started videos (autoplay first login, sidebar replay, add/replace) | Additional | PARTIAL | 6 | 18 | 16 | 2 | 6
27 | G. Add New School | “Other” school level allowing arbitrary grade mixes (P-7, P-8) | Additional | MISSING | 2 | 8 | 12 | 0 | 3
28 | H. Roles / Access Levels | Rename “Roles” → “Access Levels” throughout; show only highest level per user | Additional | MISSING | 2 | 14 | 6 | 0 | 3
29 | H. Roles / Access Levels | “Amayda” access tier above Bullyproof Admin | Additional | MISSING | 2 | 12 | 28 | 0 | 6
30 | H. Roles / Access Levels | School Licence account able to add/edit users (currently setup-only?) | Additional | PARTIAL | 0 | 5 | 12 | 0 | 3
31 | I. Branding | Logo/icon: BP → BA everywhere, animated logo, icon variants | Goodwill | PARTIAL | 36 | 30 | 0 | 6 | 6 |  | 0 | Goodwill - included at no charge (module M8; ~$9,300 of work, charged $0)
32 | J. AP Certificate | Certificate generation on course completion; accessible/downloadable | Additional | PARTIAL | 4 | 10 | 8 | 0 | 2
33 | J. AP Certificate | Uploadable/replaceable certificate template with fields (name, date, optional cert number) | Additional | MISSING | 6 | 16 | 20 | 2 | 4
34 | K. Reports (Admin) | Reports: School Status, Lesson Completion & Ratings, Culture Rating, AP Certification & Ratings | Additional | PARTIAL | 2 | 10 | 10 | 0 | 3
35 | K. Reports (Admin) | Per-report Filters panel + Export modal (CSV/Excel/PDF), export scope | Additional | MISSING | 3 | 18 | 16 | 0 | 3
36 | K. Reports (Admin) | Government stakeholder dashboards / reporting | Additional | MISSING | 10 | 28 | 28 | 0 | 8
37 | K. Reports (Admin) | Exclude “Bullyproof Academy” test school from reports | Additional | MISSING | 0 | 0 | 5 | 0 | 1
38 | L. Onboarding | Onboarding checklist: Benchmark received, Jeff Horn visit, Practical Training, Onboarding Session (dates + active/locked) | Additional | MISSING | 4 | 18 | 20 | 0 | 6
39 | L. Onboarding | (defect) School Address & Email Domain not saving on edit | Original | EXISTS | 0 | 1 | 2 | 0 | 1
40 | L. Onboarding | (defect/UX) Apply Template visual confirmation (Template Active / green) | Original | PARTIAL | 3 | 16 | 4 | 0 | 2
41 | L. Onboarding | (defect) Activity / Licence / Feature Access buttons non-functional | Additional | PARTIAL | 3 | 20 | 28 | 0 | 4
42 | L. Onboarding | Add Class: capture student numbers (Class Size field) | Additional | PARTIAL | 0 | 5 | 2 | 0 | 1
43 | M. School Portal | Remove Dashboard; role-based Home pages (Staff / AP Teacher / School Admin) | Additional | PARTIAL | 4 | 22 | 6 | 0 | 3
44 | M. School Portal | Remove Ctrl+K command menu; keep light/dark toggle | Additional | PARTIAL | 0 | 5 | 0 | 0 | 1
45 | M. School Portal | Rename Content → Preview Lessons, Lessons → Teach Lessons | Additional | PARTIAL | 0 | 5 | 0 | 0 | 1
46 | M. School Portal | Sidebar hover tooltips / screen-tips | Done/— | EXISTS | 0 | 1 | 0 | 0 | 0
47 | M. School Portal | Reports page message “available soon” | Additional | MISSING | 4 | 18 | 20 | 0 | 6
48 | M. School Portal | AP Certification page states (Start / Continue / Course Completed) | Additional | PARTIAL | 0 | 6 | 0 | 0 | 1
49 | M. School Portal | Teachers list as sortable columns + take-over-lesson workflow | Additional | PARTIAL | 3 | 24 | 16 | 0 | 4
50 | M. School Portal | Classes page star toggle (My Classes / Other Classes) | Done/— | EXISTS | 0 | 1 | 0 | 0 | 0
51 | M. School Portal | Teach Lessons defects (blank-screen, multi-level guidance, take-over, back-to-lesson) | Original | PARTIAL | 2 | 20 | 14 | 0 | 4
52 | M. School Portal | Start Now vs Schedule lesson flow; scheduling (date/time, start previously-scheduled) | Additional | PARTIAL | 2 | 16 | 6 | 0 | 2
53 | M. School Portal | Lesson recommendation issues (year ordering, loop to L1 after L10, only 3 showing, wrong lesson for mixed levels) | Original | PARTIAL | 0 | 4 | 18 | 0 | 3
54 | M. School Portal | “Start new calendar year” reset (push classes to L1, archive prior-year audit logs) | Additional | MISSING | 0 | 12 | 28 | 2 | 6
55 | M. School Portal | Lesson feedback: mandatory-rating note; default-to-5-stars option | Additional | PARTIAL | 0 | 5 | 2 | 0 | 1
56 | M. School Portal | Performance page (enter / view comparative periods) | Additional | PARTIAL | 4 | 20 | 18 | 0 | 4
57 | M. School Portal | Settings/Users, Settings/Classes (student numbers), Settings/Certification renames | Additional | PARTIAL | 2 | 18 | 8 | 0 | 4
58 | M. School Portal | Support button → mailto support@bullyproofaustralia.org.au (+cc) | Done/— | EXISTS | 0 | 0 | 0 | 0 | 0
59 | M. School Portal | School-admin reports: AP Certified Staff, AP Teacher, Class, Culture Rating (current + previous years) | Additional | MISSING | 4 | 18 | 22 | 0 | 6
60 | N. Documentation | Admin User Guide + System Administrator Guide (Word) | Additional | MISSING | 6 | 2 | 0 | 0 | 44
TOTAL (man-hours cost)

## Summary
Bullyproof — Change Request · Discipline costing
By discipline
Discipline | Hours | Day rate | Days | Cost (AUD)
Design / UX
Frontend (React/Next)
Backend
DevOps / Infra
PM / BA / Admin
TOTAL
By scope
Scope | Items | Hours | Cost (AUD) | Note
Original agreement (content + bugs) |  |  |  | Committed ~6 weeks. Item 18 content type agreed at $30k.
Additional scope (added later) |  |  |  | Billed on top, own timeline.
Goodwill - Brand Refresh (M8), no charge |  |  | 0 | Included free as a goodwill gesture; effort kept in the model but excluded from the chargeable total.
CHARGEABLE total (man-hours, ex goodwill)