## Items
Item | Section | Feature | Status | Effort | Days | Day rate | Price (AUD) | Assessment | Key files / paths
1 | A. Admin — Home / Dashboard | Admin landing / dashboard (to be replaced) | EXISTS | — | 0 | 1100 |  | The dashboard to be replaced is /dashboard (hero + 4 quick-action cards + 4 snapshot metric cards). /admin is a separate tools-launcher grid. Both render today. No build — replacement is captured by Items 2–9. | app/(main)/dashboard/page.tsx entities/dashboard/ui/admin/admin-dashboard.tsx app/(main)/admin/page.tsx
2 | A. Admin — Home / Dashboard | Total Schools vs Active (onboarding-complete) Schools | PARTIAL | M | 3.5 | 1100 |  | Total schools and an “active licence” count exist. An “active = onboarding-complete” count and Ahead/Behind summary cards do not. resolveSchoolStatus() exists but is not aggregated into a dashboard summary. | entities/dashboard/ui/admin/sections/overview/overview-section.tsx entities/dashboard/ui/admin/sections/reports/reports-overview-content.tsx
3 | A. Admin — Home / Dashboard | Per-school schedule status (On / Ahead / Slightly Behind / Behind) | MISSING | XL | 15 | 1100 |  | No schedule engine, no term-calendar table, no cadence math anywhere in code. Fully designed in the redesign docs but zero implementation. | docs/features/admin-dashboard-redesign/schedule-engine/ (design only)
4 | A. Admin — Home / Dashboard | “This School Year” / program-year selector (multi-year) | MISSING | L | 7.5 | 1100 |  | No multi-program-year selector anywhere. Reports have an all-schools / per-school scope combobox only. Depends on the program-year data model (Item 5). | entities/dashboard/ui/admin/sections/reports/reports-layout-shell.tsx
5 | A. Admin — Home / Dashboard | Data model: each school’s initial year vs ongoing years | MISSING | L–XL | 12 | 1100 |  | No program/cohort-year concept exists. The existing schoolYears table is grade levels (Year 7 etc.), and schoolYearAssignments is which grade levels a school covers — not program years. schoolLicences has start dates but no “year 1 vs year 2” model. | drizzle/schema.ts → schoolYears, schoolYearAssignments, schoolLicences
6 | A. Admin — Home / Dashboard | Sidebar items: Manage Schools / Lessons / AP Cert / Users | EXISTS | S | 1 | 1100 |  | Present as quick-action cards (mostly shipped). Classes and Lessons admin items are currently disabled in config. | entities/dashboard/ui/admin/sections/overview/overview-section.tsx lib/admin-items.ts
7 | A. Admin — Home / Dashboard | Dashboard filters: state, school level, sector, AP level, status | PARTIAL | M | 3.5 | 1100 |  | State / Sector / Status / Type filters exist on the /admin/schools table, not on a dashboard. No “AP level” filter and no Schedule filter (depends on Item 3). | entities/dashboard/ui/admin/sections/schools/schools-section.tsx
8 | A. Admin — Home / Dashboard | Dashboard columns (Culture trend, AP Cert %, Students, Classes, Teacher History, Lessons %, Schedule, Last Activity, Action) | PARTIAL | L–XL | 12 | 1100 |  | Current columns: Status, Name (opens drawer), Level, State, Sector, Staff, Teachers, Classes. The 9 requested columns are specced but unbuilt; several need new aggregation + the schedule engine + a culture indicator. Total Students has no source column today. | entities/dashboard/ui/admin/sections/schools/components/schools-table-columns.tsx docs/features/admin-dashboard-redesign/plan.md §5
9 | A. Admin — Home / Dashboard | Drill-downs: Onboarding, Culture, AP Cert detail, Class, Lesson History, Teacher History | PARTIAL | M×4 | 10 | 1100 |  | Onboarding / Culture / Class exist as drawer tabs. Lesson History, Teacher History, and per-school AP Cert % are missing. The Activity panel is a “coming soon” stub. Four drill-downs to build at ~M each. | entities/dashboard/ui/admin/sections/schools/school-detail/panels/*
10 | B. School Terms / Schedule Engine | Settings → School Terms (per-state term dates, per year, annual reset) | MISSING | L | 7.5 | 1100 |  | No term-date data model or settings UI. The states table is id/code/name only; schoolYears is grade levels, not calendar terms. Annual reset is deferred to a follow-up cron. | docs/features/admin-dashboard-redesign/schedule-engine/tdd.md (design only) no schoolTermCalendars table in drizzle/schema.ts
11 | B. School Terms / Schedule Engine | Term entry form (year/state/term dropdowns, date pickers, end-before-start validation) | MISSING | M | 3.5 | 1100 |  | No component exists. Only a generic end ≥ start pattern exists elsewhere (culture benchmarks). Assumes the term table from Item 10 exists. | (none — to be created under admin settings)
12 | B. School Terms / Schedule Engine | Schedule calculation engine (progress vs Term 2 cadence, by state terms) | MISSING | XL | 15 | 1100 |  | Fully TDD-specced (getTerm2Progress, computeClassSchedule, computeSchoolSchedule) but zero code — grep returns no implementation. School status = worst class; class status by lesson cadence vs week-of-term. | docs/features/admin-dashboard-redesign/schedule-engine/tdd.md (spec only)
13 | B. School Terms / Schedule Engine | “Progress to End of Term 2” widget (current week, % elapsed by school days) | MISSING | M | 3.5 | 1100 |  | Planned in the redesign plan (termProgress: weekOfTerm, percentElapsed). Only hardcoded “Term 1/2” copy exists today. UI-only once the engine (Item 12) exists. | docs/features/admin-dashboard-redesign/plan.md (design only)
14 | C. Culture Rating | Data entry inputs (school days, attendance, absences, incidents, suspensions S/L, exclusions) | EXISTS | S | 1 | 1100 |  | All 8 requested inputs present exactly — numeric, min 0. Built and working; only minor tweaks. | entities/dashboard/ui/admin/sections/culture/culture-rating-metrics-fields.tsx entities/culture-rating/ui/school-culture-rating-data-form.tsx
15 | C. Culture Rating | Calculation / formulas with zero-input weighting | PARTIAL | M | 3.5 | 1100 |  | Weighted headline formula built but flagged interim “fitted to the sample workbook — until the official Woodford mapping is finalised.” Zero-input handling is a null-guard (returns null) rather than a zeroed weight. | lib/culture-rating-math.ts server/culture-ratings/culture-rating-metrics.ts server/culture-ratings/culture-ratings.service.ts
16 | C. Culture Rating | Benchmark + comparative periods (storage, rules: ≥20 days, overlap, post-program) | PARTIAL | M | 3.5 | 1100 |  | ≥20-school-days and non-overlap rules enforced; comparative must start after benchmark ends. The “post-program / all-lessons-delivered” rule is explicitly NOT enforced (TODO in code). Report-request → PDF upload → download flow is built. | drizzle/schema.ts → schoolCultureBenchmarks, schoolCultureComparativePeriods server/culture-ratings/culture-rating-periods.ts
17 | C. Culture Rating | UX: comparative-period dropdown + speedometer (±100%, expandable to 150/200%) | PARTIAL | M | 3.5 | 1100 |  | Comparative-period dropdown is done. The gauge is a fixed 0–100 semicircle, not the signed ±100/150/200% improvement dial requested. The component itself notes it should be refined when the official mapping lands. | entities/culture-rating/ui/culture-rating-comparison-dashboard.tsx (SemiCircleGauge)
18 | D. Content Types (Multi-Curriculum) | Add new Content Types / curricula (name, level count, level names) | MISSING | XL | 15 | 1100 |  | Two curricula are hardcoded as concepts (Curriculum and Certification). You can add a stage within the one curriculum, but cannot define a new content-type with its own level count / level names. No parent content-type table or content_type column exists. | drizzle/schema.ts → curriculumStages, certificationCourses entities/dashboard/ui/admin/sections/content/add-stage-sheet.tsx
19 | D. Content Types (Multi-Curriculum) | Per-content-type lesson creation / upload | PARTIAL | L | 7.5 | 1100 |  | Full slide/lesson authoring exists, but only for the two fixed trees. No mechanism to spin up authoring for a new content type. | app/api/topic-slides/bulk-save/route.ts app/api/certification/topics/[topicId]/slides/bulk/route.ts
20 | D. Content Types (Multi-Curriculum) | Content Type dropdown on Add New School | MISSING | M | 3.5 | 1100 |  | The add-school wizard has Name / Level / State / Sector only. The schools table has no content-type FK. Depends on Item 18 existing first. | entities/dashboard/ui/admin/sections/schools/components/add-school-wizard.tsx
21 | D. Content Types (Multi-Curriculum) | Per-content-type resources | PARTIAL | M | 3.5 | 1100 |  | Resources scope to global vs a specific school and can be tagged to curriculum topics, but there is no link to a content-type level. (S if content-type is derived from the linked topic.) | drizzle/schema.ts → resourceFiles, resourceFileTopics, resourceFolders
22 | E. Content Management / Security | MFA on content edits (email verification code before saving) | MISSING | M | 3.5 | 1100 |  | Content edits are gated by feature permission (checkFeatureAccess) only. OTP exists at login only — never on a save action. No step-up verification. | app/api/topic-slides/bulk-save/route.ts app/api/certification/topics/[topicId]/slides/bulk/route.ts
23 | E. Content Management / Security | Sole-content-editor / content-edit permission model | PARTIAL | S–M | 3 | 1100 |  | A flexible permission gate exists (per global/role/school/user). There is no exclusive “single designated editor” lock or ownership field; multiple users can hold the permission. | server/features/features.service.ts drizzle/schema.ts → features, featurePermissions, permissionTemplates app/(main)/admin/features/
24 | E. Content Management / Security | Content audit log (create/edit/delete; date, user, event, content, version; comments) | MISSING | L | 7.5 | 1100 |  | The audit-logs admin page is a placeholder stub. No app-level audit table; content mutations only console.log (“audit trail” comments are just logging). | app/(main)/admin/audit-logs/page.tsx (stub)
25 | E. Content Management / Security | Version numbers + last-updated/updated-by per lesson/module; report; read-only retention | MISSING | L | 7.5 | 1100 |  | No version numbering anywhere on content; no updated-by attribution on topics/slides/lessons/courses; no historical retention. Some tables carry updatedAt timestamps only. | drizzle/schema.ts → topics, topicSlides, lessons, courseTopics (no version/updatedBy)
26 | F. Getting Started Videos | Role-based getting-started videos (autoplay first login, sidebar replay, add/replace) | PARTIAL | L | 7.5 | 1100 |  | One global welcome video with a binary completion flag. Not role-based, does not autoplay (requires click), no replay entry point, and not admin-manageable (URL is a hardcoded constant). | app/(main)/welcome/page.tsx (hardcoded Vimeo URL) components/organisms/vimeo-player.tsx app/api/me/tutorials/route.ts
27 | G. Add New School | “Other” school level allowing arbitrary grade mixes (P-7, P-8) | MISSING | M | 3.5 | 1100 |  | Levels are a fixed two-value enum (primary/secondary, with “Both” mapping to both). A DB CHECK constraint restricts the key. Grades bind to a level, so true arbitrary mixes are non-trivial. | components/molecules/invite-new-school-dialog.tsx:78 drizzle/schema.ts:1420 (school_levels_key_chk)
28 | H. Roles / Access Levels | Rename “Roles” → “Access Levels” throughout; show only highest level per user | MISSING | M | 3.5 | 1100 |  | Today the UI shows all roles, labelled “Roles” (~15 files). Rename is mechanical; “highest-only” can reuse existing priority maps (no migration). | lib/platform-role-order.ts components/atoms/role-badges.tsx app/(main)/admin/users/*
29 | H. Roles / Access Levels | “Amayda” access tier above Bullyproof Admin | MISSING | L | 7.5 | 1100 |  | AMAYDA exists only as course/certification content, never as a role/scope. Above PLATFORM_ADMIN there is only the internal INTRADARK_DEV. Role keys are hardcoded across many files. | server/reports/admin-reports.service.ts (AMAYDA_SLUG) server/roles/roles.repo.ts server/auth/rbac.ts
30 | H. Roles / Access Levels | School Licence account able to add/edit users (currently setup-only?) | PARTIAL | S–M | 3 | 1100 |  | User management is ongoing (a permanent settings page), not setup-only — but it is restricted to SCHOOL_ADMIN. SCHOOL_LICENCE is blocked server-side and is role-exclusive. | server/lib/can-manage-school-users.ts scripts/enforce-school-licence-constraints.sql app/(main)/schools/[school_id]/settings/users/
31 | I. Branding | Logo/icon: BP → BA everywhere, animated logo, icon variants | PARTIAL | L–XL | 12 | 0 | 0 | Goodwill - included at no charge (module M8 Brand Refresh). Effort kept; price $0. Two static logo variants (full/mark) chosen by a ternary. No animated logo, no PWA/icon variant set, no central brand constant or <Logo> component. “Bullyproof” is hardcoded ~250 times across 83 files. | public/images/bullyproof-logo.svg, bp-small-logo.svg components/organisms/app-sidebar.tsx utils/metadata.ts
32 | J. AP Certificate | Certificate generation on course completion; accessible/downloadable | PARTIAL | M | 3.5 | 1100 |  | A styled on-screen “AP Certified” card appears at 100% completion, but there is no PDF / print / image export and no persisted artifact. markCertificateIssued is defined but never called. | components/molecules/topic-certificate.tsx app/(main)/courses/[course_name]/page.tsx:734 server/course-progress/course-progress.repo.ts:156
33 | J. AP Certificate | Uploadable/replaceable certificate template with fields (name, date, optional cert number) | MISSING | L | 7.5 | 1100 |  | Design, program name and badge are hardcoded in one component. No admin upload/config UI, no certificate_templates table, no cert-number field, no storage bucket. | components/molecules/topic-certificate.tsx (hardcoded JSX) drizzle/schema.ts:1151 (certificate_type label only)
34 | K. Reports (Admin) | Reports: School Status, Lesson Completion & Ratings, Culture Rating, AP Certification & Ratings | PARTIAL | M | 3.5 | 1100 |  | Coverage exists but is split across /admin/reports, /admin/ratings and /admin/culture-ratings as raw counts (not %). Not unified/named as the four reports; no “School Status” report. | app/(main)/admin/reports/{overview,certification,onboarding,lessons} app/(main)/admin/ratings/ app/(main)/admin/culture-ratings/
35 | K. Reports (Admin) | Per-report Filters panel + Export modal (CSV/Excel/PDF), export scope | MISSING | M–L | 6 | 1100 |  | Reports have only a school-scope combobox. No filters panel and no export anywhere in admin (no jsPDF/exceljs/xlsx libs present). Export infrastructure is net-new. | entities/dashboard/ui/admin/sections/reports/reports-layout-shell.tsx
36 | K. Reports (Admin) | Government stakeholder dashboards / reporting | MISSING | L–XL | 12 | 1100 |  | The government dashboard is a placeholder text stub; the roles/government page is a static marketing mock with non-functional buttons. No live gov reporting view. | entities/dashboard/ui/government/government-dashboard.tsx (stub) app/(main)/support/roles/government/page.tsx (static)
37 | K. Reports (Admin) | Exclude “Bullyproof Academy” test school from reports | MISSING | S | 1 | 1100 |  | The seeded academy (60 classes) is counted in all reports/metrics. No test-school flag column and no exclusion filter exist. | drizzle/0014_seed_bullyproof_academy_60_classes.sql server/reports/admin-reports.repo.ts
38 | L. Onboarding | Onboarding checklist: Benchmark received, Jeff Horn visit, Practical Training, Onboarding Session (dates + active/locked) | MISSING | L | 7.5 | 1100 |  | The current checklist is Essential (Licence/Admin/Staff/Classes) + Optional (domain/address/banner/avatar). None of the requested service-delivery steps exist, and there are no completion-date fields — steps are boolean-derived from counts. | entities/dashboard/ui/admin/sections/schools/school-detail/panels/school-onboarding-panel.tsx
39 | L. Onboarding | (defect) School Address & Email Domain not saving on edit | EXISTS | S | 0.5 | 1100 |  | The full persistence chain (form → validator → repo) is intact for both fields; the defect appears already fixed in current code. Verify-only / regression. | entities/school/ui/school-details-form.tsx server/school/school.validators.ts server/school/school.repo.ts:452
40 | L. Onboarding | (defect/UX) Apply Template visual confirmation (Template Active / green) | PARTIAL | M | 3.5 | 1100 |  | A success toast fires on apply, but there is no persistent “Template Active” badge on the card or per-school, and the dialog re-opens with an empty selection (no memory of which schools already have it). | app/(main)/admin/features/permission-templates/page.tsx
41 | L. Onboarding | (defect) Activity / Licence / Feature Access buttons non-functional | PARTIAL | L | 8 | 1100 |  | Mixed: Licence and Feature Access panels are fully wired (verify only). The Activity panel is a hardcoded “coming soon” stub — the only genuinely non-functional one, and a real activity-feed build (~L). | panels/school-licence-panel.tsx (✓) panels/school-features-tab.tsx (✓) panels/school-activity-panel.tsx (stub)
42 | L. Onboarding | Add Class: capture student numbers (Class Size field) | PARTIAL | S | 1 | 1100 |  | The field exists on Edit Class (“Class Size” → studentCap) and in the table, but is absent from the Add Class dialog. It is a capacity, not enrolled count. | entities/dashboard/ui/admin/sections/schools/school-detail/panels/school-classes-panel.tsx drizzle/schema.ts:1236 (studentCap)
43 | M. School Portal | Remove Dashboard; role-based Home pages (Staff / AP Teacher / School Admin) | PARTIAL | M | 4.5 | 1100 |  | /home renders one identical layout for all roles (feature-gated only). The real role-branching logic lives in the still-present /dashboard, which is the reference pattern to port and then remove. | app/(main)/schools/[school_id]/home/page.tsx app/(main)/dashboard/page.tsx
44 | M. School Portal | Remove Ctrl+K command menu; keep light/dark toggle | PARTIAL | S | 1 | 1100 |  | The Ctrl+K command menu is still mounted in the header. The light/dark toggle already exists. Removal is just deleting the mount + component. | components/molecules/command-menu.tsx components/organisms/app-header.tsx:190
45 | M. School Portal | Rename Content → Preview Lessons, Lessons → Teach Lessons | PARTIAL | S | 1 | 1100 |  | The sidebar is renamed, but stale labels remain: the page headers still read “Content” and “Lessons” and the breadcrumb auto-capitalises the URL segment with no override. | app/(main)/schools/[school_id]/content/page.tsx:61 app/(main)/schools/[school_id]/lessons/page.tsx:620 components/molecules/breadcrumb.tsx
46 | M. School Portal | Sidebar hover tooltips / screen-tips | EXISTS | S | 0 | 1100 |  | Nav items already carry tooltips (shown when collapsed); locked items swap to a “Locked” message. Done — copy tuning only. | components/organisms/nav-main.tsx (tooltip={title})
47 | M. School Portal | Reports page message “available soon” | MISSING | L | 7.5 | 1100 |  | The school reports page is a single “Coming Soon — available after Term 1” card. None of the requested reports exist. (See Item 59.) | app/(main)/schools/[school_id]/reports/reports-page-client.tsx
48 | M. School Portal | AP Certification page states (Start / Continue / Course Completed) | PARTIAL | S | 1 | 1100 |  | Rich per-topic CTA states are already computed (Begin/Continue, Start/Continue/Retake Quiz, Review slides). There is no single course-level Start/Continue/Completed button; completion swaps in the certificate card. | app/(main)/courses/[course_name]/page.tsx
49 | M. School Portal | Teachers list as sortable columns + take-over-lesson workflow | PARTIAL | L | 7.5 | 1100 |  | Teachers render as a card grid with fixed sort — not sortable columns (a table rebuild, ~L). The take-over-lesson workflow is already fully built and feature-gated. | app/(main)/schools/[school_id]/teachers/teachers-page-client.tsx components/molecules/take-over-lesson-dialog.tsx app/api/lessons/[id]/take-over/route.ts
50 | M. School Portal | Classes page star toggle (My Classes / Other Classes) | EXISTS | S | 0 | 1100 |  | Star toggle persists via meApi.teacherClasses.toggle; the page splits into My/Other sections with an All/My/Other filter. Built and working. | app/(main)/schools/[school_id]/classes/page.tsx
51 | M. School Portal | Teach Lessons defects (blank-screen, multi-level guidance, take-over, back-to-lesson) | PARTIAL | M | 5 | 1100 |  | Multi-level guidance and take-over are built. Residual: a blank state when recommendation resolves null with no multi-stage warning; “Back to lesson” hardcodes /prepare (dead-end loop for completed lessons); history page is dummy data. | components/organisms/lesson-wizard*.tsx app/(main)/schools/[school_id]/lessons/[lesson_id]/run-lesson/page.tsx
52 | M. School Portal | Start Now vs Schedule lesson flow; scheduling (date/time, start previously-scheduled) | PARTIAL | M | 3.5 | 1100 |  | Both capabilities exist but are split: the wizard offers Prepare/Start only, while scheduling lives post-creation on prepare/run-lesson. The standalone schedule component is orphaned/dead code, and logic is duplicated. | components/organisms/lesson-wizard-schedule.tsx (orphaned) app/(main)/schools/[school_id]/lessons/[lesson_id]/prepare/page.tsx
53 | M. School Portal | Lesson recommendation issues (year ordering, loop to L1 after L10, only 3 showing, wrong lesson for mixed levels) | PARTIAL | M | 3.5 | 1100 |  | Stage-complete is handled (no silent wrap to L1). Mixed-level classes resolve to the LOWEST matching stage — the likely source of “wrong recommended lesson”. The “only 3 lessons” cap is a UI limit, not the API. | server/lessons/recommendation-engine.ts app/api/lessons/recommendations/route.ts
54 | M. School Portal | “Start new calendar year” reset (push classes to L1, archive prior-year audit logs) | MISSING | L | 7.5 | 1100 |  | Backlog only (Sprint 8 in the admin-portal sprint doc) plus informational copy in the UI. No reset / promote / archive code exists. | docs/sprints/admin-portal-sprint-jun-2026.md (planned)
55 | M. School Portal | Lesson feedback: mandatory-rating note; default-to-5-stars option | PARTIAL | S | 1 | 1100 |  | Rating is required (UI + API). There is no default-to-5-stars option — initial state is null (“Click a star to rate”). | components/organisms/lesson-feedback-form.tsx server/lesson-feedback/lesson-feedback.validators.ts
56 | M. School Portal | Performance page (enter / view comparative periods) | PARTIAL | L | 7.5 | 1100 |  | Feature-gated; renders a view-only culture-rating comparison (benchmark vs comparative). Period entry happens on settings/culture-rating, not here. No general comparative metrics. | app/(main)/schools/[school_id]/performance/performance-page-client.tsx entities/culture-rating/ui/culture-rating-comparison-dashboard.tsx
57 | M. School Portal | Settings/Users, Settings/Classes (student numbers), Settings/Certification renames | PARTIAL | M | 4.5 | 1100 |  | Users = full management. Classes = “Class Size” on Edit only (a cap, not enrolled count, and absent from Add). Certification = read-only status table; no rename/edit of certifications/topics/stages. | app/(main)/schools/[school_id]/settings/{users,classes,certification}/
58 | M. School Portal | Support button → mailto support@bullyproofaustralia.org.au (+cc) | EXISTS | S | 0 | 1100 |  | Verified: mailto support@bullyproofaustralia.org.au with cc jeff@… and Glenn@…. Wired into the sidebar Support item. Done. | lib/support.ts (SUPPORT_MAILTO)
59 | M. School Portal | School-admin reports: AP Certified Staff, AP Teacher, Class, Culture Rating (current + previous years) | MISSING | L | 7.5 | 1100 |  | None of the four named reports exist, and there is no current/previous-year selector. (A separate culture-rating report request/download flow exists under settings.) | app/(main)/schools/[school_id]/reports/reports-page-client.tsx (stub)
60 | N. Documentation | Admin User Guide + System Administrator Guide (Word) | MISSING | L | 7.5 | 1100 |  | No end-user or system-administrator guide exists. docs/ holds only developer/internal material; support/resources shows a placeholder “User Guides” card with no linked files. | docs/** (developer material only) app/(main)/support/resources/page.tsx (placeholder)
TOTAL

## Summary
Bullyproof — Change Request · Cost roll-up
Day rate (AUD) |  | 1100
Basis | Market contract rate for a senior full-stack (React/Next.js) developer billing direct as a company, AU FY25/26. Quoted ex-GST; add 10% GST on invoice. Edit cell C3 to reprice — every total recalculates.
Sec | Section | Items | Days | Price (AUD)
A | Admin — Home / Dashboard | 9 | 64.5
B | School Terms / Schedule Engine | 4 | 29.5
C | Culture Rating | 4 | 11.5
D | Content Types (Multi-Curriculum) | 4 | 29.5
E | Content Management / Security | 4 | 21.5
F | Getting Started Videos | 1 | 7.5
G | Add New School | 1 | 3.5
H | Roles / Access Levels | 3 | 14
I | Branding (incl. M8 goodwill - no charge) | 1 | 12
J | AP Certificate | 2 | 11
K | Reports (Admin) | 4 | 22.5
L | Onboarding | 5 | 20.5
M | School Portal | 17 | 62.5
N | Documentation | 1 | 7.5
TOTAL