Intradark Pty Ltd  ·  ABN 38 696 182 457

Bullyproof Platform - Change-Request Proposal

Itemised quote for the new work, with timelines and terms

| To: | Glenn Rushton - Director, Amayda Pty Ltd (ABN 45 629 524 769) |
| --- | --- |
| From: | Aaron J. Girton - Director, Intradark Pty Ltd |
| Date: | 29 June 2026 |
| Re: | Quote for the additional work in your 22 June review - priced, scoped and scheduled |

Glenn,

As requested, here is the itemised quote for the new work - each module priced and scoped so you can commission what you want, when you want. Pricing is fixed, broken down by discipline so you can see exactly what goes into each piece, at conservative senior rates. All figures are ex-GST unless stated; Intradark Pty Ltd invoices Amayda with GST added.

# 1.  How this is structured & priced

- Fixed price per module - commission any module on its own, or the whole program at a discount.

- Discipline breakdown, in hours - every module is costed by UX/design, frontend, backend, DevOps and product-management effort, task by task, at conservative senior contract hourly rates.

- Three buckets - the new work (priced below); the work that completes Phase 1 (§4 - covered by the balance already payable, not billed here); and genuine goodwill at no charge (§4).

- M1 - Content Type proceeds as separately agreed in April (§3).

Rates are conservative. Every discipline is priced at or below the bottom of the senior market band (Australian contract day rates, FY25/26 - benchmark in the appendix). Nothing here is at mid- or top-of-market.

# 2.  New-functionality modules

Eight modules - M1 is the Content Type as separately agreed in April. Each has its own detailed quote document, with a full work breakdown of what every discipline does - task by task, from schema migrations to test passes - plus an appendix quoting the excerpts of your 22 June document the module responds to, so every price traces directly to your request. The headline figures:

| # | Module | Hours | Price ex-GST | Delivery |
| --- | --- | --- | --- | --- |
| 1 | Content Type - as separately agreed (under the $30,000 cap) | 178 | $19,112.50 | ~1.5 weeks |
| 2 | Schedule Engine & School Terms | 308 | $33,481.25 | 1.5–2 weeks |
| 3 | Admin Program-Health Dashboard | 283 | $30,337.50 | 1.5 weeks |
| 4 | Reporting & Exports | 243 | $25,968.75 | 1 week |
| 5 | Content Governance & Security | 142 | $15,512.50 | 1 week |
| 6 | Culture-Rating UX Upgrade | 71 | $7,531.25 | 3–4 days |
| 7 | School Portal & Classroom | 179 | $19,137.50 | 1.5 weeks |
| 8 | Onboarding & Access Levels | 189 | $20,268.75 | 1 week |

| All eight modules at listed prices | 1,593 hours | $171,350.00 |
| --- | --- | --- |
| Everything together - 20% commitment discount |  | $137,080.00 |

The 20% discount (saving $34,270.00) applies when the whole program is commissioned together - a commitment to the working relationship. Prefer to pick and choose? Every module is simply at its listed price - the choice is yours.

# 3.  M1 - Content Type - as separately agreed

Per your email of 23 April 2026, the Content Type proceeds in its own agreement at a price not to exceed $30,000. Scoped task by task, it comes to $19,112.50 ex-GST - $10,887.50 (36%) under the cap. The same costing method and the same rate card - hours per task, per discipline - price every module in this proposal identically. Detailed in its own quote document; note Thursday Island cannot start until the Content Type is operational.

| Item |  | Price ex-GST |
| --- | --- | --- |
| Content Type (agreed - under the $30,000 cap) | ~1.5 wks | $19,112.50 |
| Class-selection guidance (optional companion piece) |  | $1,900.00 |
| Related class-selection defect fixes |  | free |

# 4.  Not billed in this quote - completing Phase 1, plus goodwill

Two kinds of work sit outside this quote, for different reasons - shown so the picture is complete:

|  | Basis | Value ex-GST |
| --- | --- | --- |
| Outstanding contract work (culture calc, functional reporting, certificates, documentation) | Original agreement | $13,662.50 |
| Genuine defects (address save, template feedback, Teach-Lessons, recommendation, user-column sort arrows, Global Resources investigation) | Warranty | $10,068.75 |
| Completing Phase 1 - covered by the balance payable under the agreement (§7) |  | $23,731.25 |
| Brand Refresh (BP to BA) (rebrand, animated logo, icon set, teal sidebar) | Goodwill | $8,062.50 |
| Certificate of Achievement template (uploadable/replaceable, with name, date and certificate-number fields) | Goodwill | $5,162.50 |
| Remove the Ctrl+K command menu | Goodwill | $625.00 |
| Goodwill - genuinely at no charge |  | $13,850.00 |

To be clear about the first group: it is not a gift. It is the remaining delivery under the original agreement - the work that earns the Phase-1 balance in Section 7. The second group is genuinely free.

# 5.  Timeline

- M1 - Content Type: ~1.5 weeks from commissioning - noting Thursday Island cannot start until it is operational.

- Order is yours: modules are priced independently - choose what matters most and the sequence. The one dependency: the Schedule Engine (M2) underpins the Dashboard (M3).

Dependencies at a glance - what needs what:

| Module | Needs first | From your side |
| --- | --- | --- |
| M1 - Content Type | None - fully standalone | Thursday Island lesson content |
| M2 | None - the foundation | Confirmed ACT Term 3 dates |
| M3 | M2 (engine + program-year model) | - |
| M4 | None to start; Schedule filter + prior-year selection activate once M2 exists | - |
| M5 | None | - |
| M6 | None | 25 April weighting confirmed as final |
| M7 | None to start; year selector + calendar-year reset use M2 | - |
| M8 | None | The three Getting Started videos |

- Main program: 8–9 weeks of intensive, extended-hours delivery. I will push to bring this in ahead of schedule - targeting ~6 weeks - as a best-efforts commitment to your momentum, at no extra cost.

# 6.  Payment

- 40% deposit on commissioning; balance by milestone payments through delivery.

- Deposit invoices raised on commissioning.

- Invoiced by Intradark Pty Ltd, +GST; deployment/handover on payment.

# 7.  Engagement structure & the Phase-1 account

## (a)  Moving to a full contract basis

The salary arrangement served its purpose while Phase 1 was being built, but it blurs two things that should be clean: employment, and a fixed-price development contract. I would like to end it and run the whole engagement through Intradark Pty Ltd on invoices - deposits up front, milestone / module payments on delivery, all +GST - starting with this proposal. Practically: we agree a cessation date, payroll reconciles final pay, superannuation and leave, and the unconsumed portion of the salary component converts to contract invoicing.

This also speaks to the key-personnel point you have raised. Intradark has grown: I have brought on multiple new hires, including a developer in training who you will meet as I onboard him to the Bullyproof project. The engagement structure should reflect what it now is - a company delivering with a team, not a dependency on one individual.

## (b)  Phase-1 account position (as at 10 June 2026)

Phase 1 was engaged at $250,000 in two parts: the $150,000 + GST fixed fee under the signed Variation, and a $100,000 salary component (via Bullyproof Australia payroll).

|  | Amount | Basis |
| --- | --- | --- |
| Fixed fee (Variation cl 4) | $150,000 + GST | Signed Variation, 23 April 2026 |
| Received - deposit on signing | $50,000 + GST ($55,000) | cl 4(a) - paid |
| Balance - on completion & handover | $100,000 + GST | cl 4(b) - falls due at Final Acceptance |
| Salary component | $100,000 | Bullyproof Australia payroll |
| Drawn to 10 June 2026 | $72,348.50 gross | per payslip; super + accrued leave also count toward the component, per your advice |
| Remainder - converts at cessation | $100,000 − gross drawn − super/leave per payroll − pay cycles to cessation | invoiced by Intradark at cessation |

## (c)  The completion path

I complete all remaining in-scope work and every genuine defect fix (Section 4) as part of delivering Phase 1 - the work the outstanding balance already covers - through to Final Acceptance and full handover under cl 4(b), at which point that balance falls due as agreed. The new work in this proposal sits entirely on top, billed only as commissioned.

# 8.  The numbers, together

| Scenario | ex-GST | inc-GST |
| --- | --- | --- |
| All eight modules at listed prices | $171,350.00 | $188,485.00 |
| Everything together - 20% commitment discount | $137,080.00 | $150,788.00 |
| Optional add-on: multi-class selection guidance | $1,900.00 | $2,090.00 |

These figures cover the new work only. The Phase-1 completion work in Section 4 ($23,731.25) is covered by the balance in Section 7 - not billed here, and not a gift. A further $13,850.00 of goodwill work is included at no charge.

# 9.  Next steps

- Tell me which modules you want (or the whole program for the 20% bundle), and I raise the deposit invoices.

- The Content Type can start immediately on deposit - Thursday Island cannot begin until it is operational.

- Confirm a cessation date for the salary arrangement (Section 8) so payroll can reconcile super and leave, and I can issue the conversion invoice.

- Happy to walk through any module on a call.

# Appendix - rate evidence & market comparison

Published Australian contract rates, verified live on 2 July 2026 - every source below is a public page you can open. Because one person leads every discipline on this engagement, the honest comparator is the lead / principal rate for each discipline - yet this proposal is priced below the senior floor, two tiers under the seat actually being filled. (Several cited figures are “rate to the contractor” including superannuation on an 8-hour day, per the source pages - which makes this comparison conservative.)

## Product Mgmt / BA   -   this proposal: $93.75/hr  ($750/day)

| Source | Role / level | Published rate | Link |
| --- | --- | --- | --- |
| Morgan McKinley 2026 | Lead Business Analyst | $1,050 – 1,250/day | morganmckinley.com/au/salary-guide/projects-strategy-change/contract-salaries |
| Clicks IT | Delivery Lead | $1,140 – 1,350/day | clicks.com.au/job-salary/delivery-lead |
| Clicks IT | Product Manager (senior - no lead tier published) | $985/day | clicks.com.au/job-salary/product-manager |

## UX / Design   -   this proposal: $100.00/hr  ($800/day)

| Source | Role / level | Published rate | Link |
| --- | --- | --- | --- |
| Clicks IT | UX/UI Architect | $1,040 – 1,245/day | clicks.com.au/job-salary/ux-ui-architect |
| Morgan McKinley 2026 | Product Designer (high of range) | $1,100/day | morganmckinley.com/au/salary-guide/technology/contract-salaries |
| Clicks IT | UX/UI Designer (senior) | $1,040/day | clicks.com.au/job-salary/ux-ui-designer |

## Frontend   -   this proposal: $106.25/hr  ($850/day)

| Source | Role / level | Published rate | Link |
| --- | --- | --- | --- |
| Morgan McKinley 2026 | Software Development Team Lead | $1,000 – 1,250/day | morganmckinley.com/au/salary-guide/technology/contract-salaries |
| Clicks IT | Technical Lead | $1,140/day (senior) | clicks.com.au/job-salary/technical-lead |
| Clicks IT | React Developer (senior) | $1,040/day | clicks.com.au/job-salary/react-developer |

## Backend   -   this proposal: $112.50/hr  ($900/day)

| Source | Role / level | Published rate | Link |
| --- | --- | --- | --- |
| Clicks IT | Back End Developer (senior) | $1,400/day | clicks.com.au/job-salary/back-end-developer |
| Morgan McKinley 2026 | Software Development Team Lead | $1,000 – 1,250/day | morganmckinley.com/au/salary-guide/technology/contract-salaries |
| Talent International (Mar 2026) | Principal Engineer (ceiling reference) | $1,456/day | talentinternational.com/blog/top-tech-contractor-day-rates-australia |

## DevOps / Infra   -   this proposal: $118.75/hr  ($950/day)

| Source | Role / level | Published rate | Link |
| --- | --- | --- | --- |
| Latitude IT (May 2026) | Lead / Principal (10+ yrs) | $1,200 – 1,500/day | latitudeit.com.au - DevOps salary 2026 |
| Morgan McKinley 2026 | DevOps Engineer (high) / Cloud Platform (high) | $1,500 / $1,600/day | morganmckinley.com/au/salary-guide/technology/contract-salaries |
| Clicks IT | DevOps Engineer (senior) | $1,245/day | clicks.com.au/job-salary/devops-engineer |

## What this program would cost at lead market rates

Priced at the bottom of the published lead bands above - i.e. the cheapest lead-level market scenario, before agency margins:

| Discipline | Hours | Lead rate (low) | At lead market | This proposal |
| --- | --- | --- | --- | --- |
| UX / Design | 126 h | $130.00/hr | $16,380.00 | $12,600.00 |
| Frontend | 573 h | $137.50/hr | $78,787.50 | $60,881.25 |
| Backend | 707 h | $125.00/hr | $88,375.00 | $79,537.50 |
| DevOps / Infra | 32 h | $150.00/hr | $4,800.00 | $3,800.00 |
| Product Mgmt / BA | 155 h | $131.25/hr | $20,343.75 | $14,531.25 |

| All eight modules at lead market rates (low end) |  | $208,686.25 |
| --- | --- | --- |
| This proposal - listed prices | saves $37,336.25 | $171,350.00 |
| This proposal - with the 20% commitment discount | saves $71,606.25 | $137,080.00 |

Respect always,

Aaron J. Girton

Director, Intradark Pty Ltd

agirton@intradark.com