Intradark Pty Ltd  ·  ABN 38 696 182 457

Quote - M8: Onboarding & Access Levels

Bullyproof platform - new-functionality module

| To: | Glenn Rushton - Director, Amayda Pty Ltd |
| --- | --- |
| From: | Aaron J. Girton, Intradark Pty Ltd |
| Date: | 29 June 2026 |
| Module: | M8 of 8 - commissionable independently |

# Scope

Onboarding and roles - the service-step checklist with dates, role-based Getting Started videos, the “Other” school level, School-Licence user management, and the new “Amayda” access tier.

## What this module delivers

- Role-based Getting Started videos - first-login autoplay, replay, admin add/replace

- “Other” school level allowing arbitrary grade mixes (e.g. P-7, P-8)

- “Amayda” access tier sitting above Bullyproof Admin

- School-Licence account able to add/edit users (relaxing setup-only)

- Onboarding service-step checklist - Benchmark received, Jeff Horn visit, Practical Training, Onboarding Session - with completion dates

Also included in this module’s scope:

- School-portal Access-Level dropdown limited to Staff / AP Teacher / School Admin only

# Effort & price

Fixed price, broken down by discipline at conservative senior contract rates (ex-GST):

| Discipline | Hours | Hourly rate | Subtotal |
| --- | --- | --- | --- |
| UX / Design | 14 h | $100.00/hr | $1,400.00 |
| Frontend | 61 h | $106.25/hr | $6,481.25 |
| Backend | 88 h | $112.50/hr | $9,900.00 |
| DevOps / Infra | 2 h | $118.75/hr | $237.50 |
| Product Mgmt / BA | 24 h | $93.75/hr | $2,250.00 |

| Module total | 189 hours | $20,268.75 |
| --- | --- | --- |
| + GST (10%) |  | $2,026.88 |
| Total inc GST |  | $22,295.63 |

# Work breakdown - what each discipline does

Indicative basis of estimate. This is the engineering work behind the fixed price - itemised task by task so the effort is visible. It is not a deliverables checklist, tasks are not individually severable from the fixed price, and it does not change the acceptance basis; the deliverable is the working module described above.

| UX / Design - $100.00/hr | Est. hours |
| --- | --- |
| Wireframe onboarding service-step checklist with date states (done, pending, optional Jeff Horn) | 3 |
| Design Getting Started video modal (3 role variants), first-login autoplay + sidebar replay entry | 3 |
| Design P-12 grade-mix picker for 'Other' school level (forms + level badge treatment) | 2.5 |
| Design school-licence user management sheet + School Admin recovery dialog states | 3.5 |
| Design QA review of built M7 screens vs specs, responsive + dark-mode variants | 2 |
| Subtotal | 14 h · $1,400.00 |

| Frontend - $106.25/hr | Est. hours |
| --- | --- |
| Rebuild school-onboarding-panel.tsx with 4 service steps + completion date pickers | 6 |
| Render Jeff Horn visit as optional so it never blocks Active status in onboarding/activation panels | 1.5 |
| Add TanStack Query hooks in entities/school/api for onboarding steps with optimistic date updates | 4 |
| Refactor app/(main)/welcome/page.tsx to load role-matched video from API (drop hardcoded Vimeo URL) | 4 |
| Wire first-login autoplay off metadata.tutorials flag via useMeStore + useCompleteTutorial | 3 |
| Add Getting Started replay entry under Support in components/organisms/app-sidebar.tsx | 1 |
| Build admin Getting Started video manager page (list/add/delete per role) under app/(main)/admin | 6 |
| Create entities/getting-started/api endpoints.ts + model/keys.ts query hooks | 3 |
| Add 'Other' level option with P-12 grade multi-select to school create/edit forms | 5 |
| Update school level badge rendering (school-detail panels, schools table) for Other grade mixes | 3 |
| Limit school-portal access-level dropdown in add-user-sheet.tsx to TEACHER/SCHOOL_ADMIN/SCHOOL_STAFF | 2 |
| Build School Admin recovery UI (promote/re-invite dialog) in school-users-panel.tsx | 5 |
| Gate school user management UI via use-can-edit-school-roles hook + FeatureGuard | 2.5 |
| Surface Amayda tier in user-detail-drawer + platform-role-swap-dialog with edit guard rails | 4 |
| Add loading/empty/error states (skeletons, toasts) for checklist, video manager, user sheets | 3.5 |
| Vitest component tests: role-video matching, onboarding step states, role dropdown filtering | 4.5 |
| Responsive + dark-mode pass across onboarding, welcome, video manager and user screens | 3 |
| Subtotal | 61 h · $6,481.25 |

| Backend - $112.50/hr | Est. hours |
| --- | --- |
| Add school_onboarding_steps table (step_key, completed_at) to drizzle/schema.ts + SQL migration 0028 | 4.5 |
| Seed 4 service steps (benchmark_received, jeff_horn_visit, practical_training, onboarding_session) | 1.5 |
| Build server/school-onboarding/{service,repo,validators}.ts with zod completion-date validation | 6 |
| Add GET/PATCH app/api/schools/[schoolId]/onboarding-steps/route.ts gated to platform admin roles | 3.5 |
| Exclude optional jeff_horn_visit from Active-status logic in server/school/school.service.ts | 2.5 |
| Create getting_started_videos table (role_variant, video_url, sort) + RLS migration | 3.5 |
| Build server/getting-started-videos/{service,repo,validators}.ts with zod URL + role-enum checks | 4 |
| Add admin CRUD routes app/api/admin/getting-started-videos/route.ts and [id]/route.ts | 3.5 |
| Extend me.service.ts/me.repo.ts to persist per-user getting-started seen flag in user metadata | 3 |
| Add role-matched video resolver endpoint app/api/me/getting-started-video/route.ts (3 variants) | 3 |
| Migration relaxing school_levels_key_chk CHECK to allow 'other' + P-12 grade-mix storage | 4.5 |
| Extend server/school-levels service/repo/validators for arbitrary grade mixes; rebuild v_school_level_badge | 7 |
| Update schedule/completion denominator queries to count year levels from Other grade mix | 6 |
| Add school-portal user endpoints POST/PATCH app/api/schools/[schoolId]/users for licence accounts | 6 |
| Build School Admin recovery endpoint (re-invite/promote) via server/invites + user-roles routes | 5 |
| Restrict school-scope role assignment to TEACHER/SCHOOL_ADMIN/SCHOOL_STAFF in roles.validators.ts | 2 |
| Seed AMAYDA platform role above PLATFORM_ADMIN via roles + permission_templates migration | 3.5 |
| Extend ALL_PLATFORM_ADMIN_KEYS and tier precedence in server/auth/rbac.ts for AMAYDA | 5 |
| Block lower tiers from editing AMAYDA users via guard checks in roles.service.ts | 3.5 |
| Write RLS policies (has_any_role) for school_onboarding_steps + getting_started_videos | 2.5 |
| Vitest: onboarding service optional-step logic + school-levels grade-mix validators | 4 |
| Vitest: rbac AMAYDA precedence, school-role restriction, video role resolution | 4 |
| Subtotal | 88 h · $9,900.00 |

| DevOps / Infra - $118.75/hr | Est. hours |
| --- | --- |
| Apply M7 migrations (CHECK relax, new tables, AMAYDA grants) to staging then prod Supabase | 1 |
| Run Supabase advisors post-migration; smoke-test RLS on new tables and document rollback | 1 |
| Subtotal | 2 h · $237.50 |

| Product Mgmt / BA - $93.75/hr | Est. hours |
| --- | --- |
| Confirm onboarding step rules with client (date semantics, Jeff Horn visit optionality) | 2.5 |
| Collect 3 role-variant Getting Started videos and intro copy from client | 2 |
| Author Amayda vs Bullyproof Admin permission matrix and circulate for approval | 5.5 |
| Write M7 test plan covering onboarding, videos, Other level, user mgmt, Amayda tier | 5.5 |
| Coordinate UAT with a pilot School Admin (add users, recovery, first-login video) | 6 |
| Compile M7 release notes and secure acceptance sign-off | 2.5 |
| Subtotal | 24 h · $2,250.00 |

# Delivery & terms

- Indicative delivery: 1 week of focused build.

- Payment: 40% deposit on commissioning, balance by milestone on delivery & acceptance.

- Dependencies: None.

- From your side: The three Getting Started videos (Staff / AP Teacher / School Admin).

- Invoiced by Intradark Pty Ltd (+GST); deployment on payment.

Bundle option. Commission the full program together and this module is included at a 20% discount - see the Master Proposal.

# Appendix - your request, in your words

Excerpts from your document of 22 June 2026 that this quote responds to:

“I am in the process of completing a short Getting Started video for Staff, AP Teachers and School Admin and would like these to load to the Home page when Users first log in.”

“As the only directors of Amayda Pty Ltd, who own the technology and content, Jeff and I should have an “Amayda” access level that sits above Bullyproof, which would be useful for future licensing.”

“In “Level” we should also allow for “Other” schools in case they are not Primary, Secondary, P-10 or P-12. For example, what if they are P-7?”

“A School Licence access level should allow this user to add/edit Users, as they will need it to add themselves if the previous principal was the only School Admin.”

“You could possibly have it so that it checks the above boxes when they are done. There are some steps missing from the current portal. For example: Benchmark (Behaviour) Data received, Jeff Horn Visit done, Practical Training completed, Onboarding Session completed. … We could possibly add the date each step was done.”

Respect always,

Aaron J. Girton

Director, Intradark Pty Ltd

agirton@intradark.com